## Dashboard
PCIO Risk, KPI & ROI Dashboard / 风险、KPI与ROI总览
Selected risks / 已筛选风险 |  | High & critical / 高及极高 |  | Recommended KPIs / KPI建议 | Payback months / 回收期
10 |  | 9 |  | 8 | 16.1-26.2
Likelihood / 概率 | Impact 1 / 影响1 | Impact 2 / 影响2 | Impact 3 / 影响3 | Impact 4 / 影响4
4 | - | - | O02 E02 H02 | T04 T01 H03 T02
3 | - | O01 | T03 E03 | -
2 | - | - | - | -
1 | - | - | - | -
4×4 score = likelihood × impact. IDs map to Risk_Register.
Risk category / 风险类别 | Count / 数量
Technical / 技术 | 4
Organisational / 组织 | 2
Workforce / 人力 | 2
External / 外部 | 2

## Risk_Register
Rank | ID | Category | Risk ZH | Risk EN | PCIO layers | Likelihood | Impact | Score | Band | PDCA | Mitigation ZH | Mitigation EN | Profile drivers | Highlighted
1 | T04 | Technical / 技术 | 基础数据未达门槛即上线高级优化 | Advanced optimisation deployed before foundation gates are met | O,P,C,I | 4 | 4 | 16 | Critical / 极高 | Plan/Act | 把数据完整率、连接稳定性、语义一致性和人工回退设为模型上线门槛。 | Make completeness, connectivity, semantics, and human rollback mandatory model-deployment gates. | equipment_downtime,process_variation | TRUE
2 | T01 | Technical / 技术 | 关键测点覆盖、校准或数据完整性不足 | Insufficient critical-tag coverage, calibration, or completeness | P | 4 | 4 | 16 | Critical / 极高 | Plan/Do | 冻结关键测点清单，记录量程、单位、校准、缺失和责任人；先补瓶颈设备。 | Freeze the critical-tag list and record range, unit, calibration, missingness, and ownership; start with bottleneck assets. | energy_cost,process_variation | TRUE
3 | H03 | Workforce / 人力 | 自动建议的授权、确认和安全责任边界不清 | Unclear authority, confirmation, and safety accountability for automated recommendations | O,H | 4 | 4 | 16 | Critical / 极高 | Plan/Act | 明确建议、批准、执行、回退和审计责任；安全相关动作必须由合格人员确认。 | Define recommendation, approval, execution, rollback, and audit ownership; qualified personnel confirm safety actions. | process_variation | TRUE
4 | T02 | Technical / 技术 | 采集链路中断、延迟或网络隔离不足 | Collection interruption, latency, or inadequate network segregation | C | 4 | 4 | 16 | Critical / 极高 | Do/Check | 建立断点续传、链路健康监控和网络分区；保留人工回退与本地缓存。 | Use store-and-forward, link-health monitoring, and network segmentation with manual fallback and local buffering. | equipment_downtime | TRUE
5 | O02 | Organisational / 组织 | KPI 口径或收益基线不可复算 | Non-reproducible KPI definitions or benefit baseline | I,O | 4 | 3 | 12 | Critical / 极高 | Plan/Check | 冻结基线时间窗、产品组合、分母、异常剔除和财务确认规则。 | Freeze the baseline window, product mix, denominator, exclusions, and finance sign-off rules. | energy_cost,equipment_downtime | FALSE
6 | E02 | External / 外部 | 本地备件、校准或运维支持响应不足 | Insufficient local spare-parts, calibration, or maintenance response | P,C | 4 | 3 | 12 | Critical / 极高 | Plan/Do | 确定关键备件、校准周期、服务等级和本地替代方案，并纳入总拥有成本。 | Define critical spares, calibration cycles, service levels, and local alternatives in total cost of ownership. | energy_cost,equipment_downtime | FALSE
7 | H02 | Workforce / 人力 | 报警过多、误报或新增记录负担导致弃用 | Alert overload, false positives, or added recording burden causes abandonment | O,H | 4 | 3 | 12 | Critical / 极高 | Check/Act | 按风险分级报警，跟踪误报率和处置时间；取消等量重复记录。 | Tier alerts by risk, track false positives and response time, and remove equivalent duplicate recording. | equipment_downtime | FALSE
8 | T03 | Technical / 技术 | 设备、批次、工单和异常语义不一致 | Inconsistent asset, batch, work-order, and exception semantics | I | 3 | 3 | 9 | High / 高 | Plan/Check | 建立轻量数据字典、唯一编码和 KPI 公式；每次接口变更执行对账。 | Create a lightweight data dictionary, unique identifiers, and KPI formulas; reconcile every interface change. |  | FALSE
9 | E03 | External / 外部 | 网络安全、合规或区域基础设施约束 | Cybersecurity, compliance, or regional infrastructure constraints | C,O | 3 | 3 | 9 | High / 高 | Plan/Check | 由企业 IT/EHS 审核网络、账号、日志、数据保存和远程访问；必要时采用本地离线部署。 | Have corporate IT/EHS review networks, accounts, logs, retention, and remote access; use local offline deployment where needed. |  | FALSE
10 | O01 | Organisational / 组织 | 试点边界、责任人和异常关闭权责不清 | Unclear pilot boundary, ownership, and exception closure authority | I,H | 3 | 2 | 6 | Moderate / 中 | Plan | 定义单一试点边界、RACI、异常升级路径和联合签字门槛。 | Define one pilot boundary, RACI, escalation path, and joint approval gates. |  | FALSE

## Risk_Matrix_4x4
Likelihood \ Impact | 1 | 2 | 3 | 4
4 | - | - | O02 E02 H02 | T04 T01 H03 T02
3 | - | O01 | T03 E03 | -
2 | - | - | - | -
1 | - | - | - | -

## KPI_Recommendations
Rank | Priority | KPI ID | PCIO | KPI ZH | KPI EN | Current maturity | Operational baseline | Target low | Target high | Unit | Direction | Horizon | Rationale ZH | Rationale EN | Expected outcome ZH | Expected outcome EN | Evidence
1 | urgent | KPI-B-03 | O | 非计划停机时间 | Unplanned downtime | 2.8551 | 现场数据待确认 / Operational baseline required | 5 | 12 | % reduction | lower | 12 weeks / 12周试点 | 以统一停机原因和连续基线验证规则报警价值。 | Use standard downtime reasons and a continuous baseline to validate alert value. |  |  | Toolkit planning scenario (P)
2 | urgent | KPI-B-01 | P | 关键工艺参数波动幅度 | Critical process-parameter variation | 2.915 | 现场数据待确认 / Operational baseline required | 10 | 20 | % reduction | lower | 12 weeks / 12周试点 | 先验证测点和回路，再评估更严格的控制目标。 | Validate tags and loops before evaluating tighter control targets. | ±0.5℃仅作为基础门槛通过后的挑战参考。 | ±0.5°C is a stretch reference only after foundation gates pass. | PCIO-E008 (E2) adjusted as planning scenario (P)
3 | urgent | KPI-B-02 | P | 单位产品蒸汽/能源消耗 | Steam or energy consumption per unit | 2.915 | 现场数据待确认 / Operational baseline required | 7.56 | 11.24 | % reduction | lower | 12 weeks / 12周试点 | 以分项计量和同产品基线验证能源改善。 | Validate energy improvement with sub-metering and comparable product baselines. |  |  | PCIO-E009 (E2) adjusted as planning scenario (P)
4 | high | KPI-I-01 | I | 关键测点与设备/批次/工单映射完整率 | Completeness of tag-to-asset/batch/work-order mapping | 2.8472 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 当前集成能力决定统计结果能否回到具体业务情境。 | Integration determines whether analysis can be traced back to business context. |  |  | Toolkit operating target (P)
5 | high | KPI-O-01 | O | 异常闭环按期完成率 | On-time exception closure rate | 2.8551 | 现场数据待确认 / Operational baseline required | 80 | 90 | % | higher | 12 weeks / 12周试点 | 优化层先验证规则和行动闭环，再进入高级模型。 | Optimisation should validate rules and action closure before advanced models. |  |  | Toolkit operating target (P)
6 | high | KPI-P-01 | P | 关键测点有效覆盖率 | Valid coverage of critical tags | 2.915 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 感知层是后续连接、集成和优化的输入门槛。 | Perception is the input gate for connectivity, integration, and optimisation. |  |  | External n=52 Sensor_Inf=4.5077 reference + project score
7 | medium | KPI-C-01 | C | 试点数据采集可用率 | Pilot data-acquisition availability | 3.283 | 现场数据待确认 / Operational baseline required | 97 | 99 | % | higher | 12 weeks / 12周试点 | 用链路可用率代替“已联网”这一不可审计描述。 | Use measurable link availability rather than a binary 'connected' claim. |  |  | Toolkit operating target (P)
8 | medium | KPI-H-01 | H | 目标岗位任务验证通过率 | Task-based competence pass rate for target roles | 3.1092 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 培训完成不等于会用，以真实任务验证人机协同能力。 | Training completion is not competence; verify with real tasks. |  |  | Toolkit operating target (P)

## ROI_Calculator
Editable ROI Calculator / 可编辑 ROI 快速估算
Investment / 投资 | 300000
Annual addressable value / 年度可改善价值池 | 2400000
Annual operating cost / 年度运维成本 | 45000
Improvement low % / 改善下限 | 7.6%
Improvement high % / 改善上限 | 11.2%
Horizon years / 评估年数 | 3
Scenario | Improvement | Gross benefit/year | Net benefit/year | Payback months | ROI over horizon
Conservative
Base
Optimistic
Break-even improvement / 盈亏平衡改善率
Boundary / 边界 | 回收期为简单静态估算，未计税、折旧、资金成本、停产损失或爬坡曲线。 / Payback is a simple static estimate excluding tax, depreciation, cost of capital, downtime, and ramp-up.