## Dashboard
PCIO Risk, KPI & ROI Dashboard / 风险、KPI与ROI总览
Selected risks / 已筛选风险 |  | High & critical / 高及极高 |  | Recommended KPIs / KPI建议 | Payback months / 回收期
10 |  | 9 |  | 8 | 18.0-48.0
Likelihood / 概率 | Impact 1 / 影响1 | Impact 2 / 影响2 | Impact 3 / 影响3 | Impact 4 / 影响4
4 | - | - | O03 T03 E01 H01 O01 O02 H03 T01 T02 | -
3 | - | E02 | - | -
2 | - | - | - | -
1 | - | - | - | -
4×4 score = likelihood × impact. IDs map to Risk_Register.
Risk category / 风险类别 | Count / 数量
Technical / 技术 | 3
Organisational / 组织 | 3
Workforce / 人力 | 2
External / 外部 | 2

## Risk_Register
Rank | ID | Category | Risk ZH | Risk EN | PCIO layers | Likelihood | Impact | Score | Band | PDCA | Mitigation ZH | Mitigation EN | Profile drivers | Highlighted
1 | O03 | Organisational / 组织 | 跨班组或跨部门流程未同步调整 | Cross-shift or cross-department process not changed with the tool | H,I | 4 | 3 | 12 | Critical / 极高 | Do/Act | 同步修订交接班、纸质记录、异常会议和标准作业，避免数字化与旧流程并行重复。 | Update handover, paper records, exception meetings, and standard work to avoid duplicate old and digital processes. | collaboration,manual_records,schedule_changeover | TRUE
2 | T03 | Technical / 技术 | 设备、批次、工单和异常语义不一致 | Inconsistent asset, batch, work-order, and exception semantics | I | 4 | 3 | 12 | Critical / 极高 | Plan/Check | 建立轻量数据字典、唯一编码和 KPI 公式；每次接口变更执行对账。 | Create a lightweight data dictionary, unique identifiers, and KPI formulas; reconcile every interface change. | collaboration,manual_records | TRUE
3 | E01 | External / 外部 | 供应商锁定、封闭协议或数据不可迁移 | Vendor lock-in, closed protocols, or non-portable data | C,I | 4 | 3 | 12 | Critical / 极高 | Plan | 优先开放协议、可导出数据和接口验收条款；保留替代供应商清单。 | Prefer open protocols, exportable data, and interface acceptance clauses; retain alternative suppliers. | manual_records | TRUE
4 | H01 | Workforce / 人力 | 一线人员培训、使用能力或参与度不足 | Insufficient frontline training, capability, or participation | H | 4 | 3 | 12 | Critical / 极高 | Do/Check | 采用岗位化微培训、现场辅导和超级用户机制，培训后用真实任务验证。 | Use role-based micro-training, floor coaching, and super-users; verify learning with real tasks. | collaboration,manual_records | TRUE
5 | O01 | Organisational / 组织 | 试点边界、责任人和异常关闭权责不清 | Unclear pilot boundary, ownership, and exception closure authority | I,H | 4 | 3 | 12 | Critical / 极高 | Plan | 定义单一试点边界、RACI、异常升级路径和联合签字门槛。 | Define one pilot boundary, RACI, escalation path, and joint approval gates. | collaboration | FALSE
6 | O02 | Organisational / 组织 | KPI 口径或收益基线不可复算 | Non-reproducible KPI definitions or benefit baseline | I,O | 4 | 3 | 12 | Critical / 极高 | Plan/Check | 冻结基线时间窗、产品组合、分母、异常剔除和财务确认规则。 | Freeze the baseline window, product mix, denominator, exclusions, and finance sign-off rules. | quality_defects | FALSE
7 | H03 | Workforce / 人力 | 自动建议的授权、确认和安全责任边界不清 | Unclear authority, confirmation, and safety accountability for automated recommendations | O,H | 4 | 3 | 12 | Critical / 极高 | Plan/Act | 明确建议、批准、执行、回退和审计责任；安全相关动作必须由合格人员确认。 | Define recommendation, approval, execution, rollback, and audit ownership; qualified personnel confirm safety actions. | quality_defects | FALSE
8 | T01 | Technical / 技术 | 关键测点覆盖、校准或数据完整性不足 | Insufficient critical-tag coverage, calibration, or completeness | P | 4 | 3 | 12 | Critical / 极高 | Plan/Do | 冻结关键测点清单，记录量程、单位、校准、缺失和责任人；先补瓶颈设备。 | Freeze the critical-tag list and record range, unit, calibration, missingness, and ownership; start with bottleneck assets. | quality_defects | FALSE
9 | T02 | Technical / 技术 | 采集链路中断、延迟或网络隔离不足 | Collection interruption, latency, or inadequate network segregation | C | 4 | 3 | 12 | Critical / 极高 | Do/Check | 建立断点续传、链路健康监控和网络分区；保留人工回退与本地缓存。 | Use store-and-forward, link-health monitoring, and network segmentation with manual fallback and local buffering. | manual_records | FALSE
10 | E02 | External / 外部 | 本地备件、校准或运维支持响应不足 | Insufficient local spare-parts, calibration, or maintenance response | P,C | 3 | 2 | 6 | Moderate / 中 | Plan/Do | 确定关键备件、校准周期、服务等级和本地替代方案，并纳入总拥有成本。 | Define critical spares, calibration cycles, service levels, and local alternatives in total cost of ownership. |  | FALSE

## Risk_Matrix_4x4
Likelihood \ Impact | 1 | 2 | 3 | 4
4 | - | - | O03 T03 E01 H01 O01 O02 H03 T01 T02 | -
3 | - | E02 | - | -
2 | - | - | - | -
1 | - | - | - | -

## KPI_Recommendations
Rank | Priority | KPI ID | PCIO | KPI ZH | KPI EN | Current maturity | Operational baseline | Target low | Target high | Unit | Direction | Horizon | Rationale ZH | Rationale EN | Expected outcome ZH | Expected outcome EN | Evidence
1 | urgent | KPI-B-05 | I | 人工重复记录时间 | Duplicate manual recording time | 2.5768 | 现场数据待确认 / Operational baseline required | 15 | 30 | % reduction | lower | 12 weeks / 12周试点 | 数字化上线时同步取消等量重复纸质步骤。 | Retire equivalent duplicate paper steps when digital capture goes live. |  |  | Toolkit planning scenario (P)
2 | urgent | KPI-B-04 | O | 返工/缺陷率 | Rework or defect rate | 2.6725 | 现场数据待确认 / Operational baseline required | 5 | 10 | % reduction | lower | 12 weeks / 12周试点 | 保持产品组合和检验口径一致。 | Hold product mix and inspection definitions constant. |  |  | Toolkit planning scenario (P)
3 | urgent | KPI-B-06 | P | 瓶颈设备状态感知覆盖率 | State-sensing coverage for bottleneck assets | 2.7767 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 柔性较低时先补齐设备状态、节拍、等待和停机原因，而不是直接上排产 AI。 | When flexibility is low, capture state, cycle, waiting, and downtime reasons before scheduling AI. | 柔性绩效问卷分数试点提升 0.2-0.5/5，须与换产/等待时间交叉验证。 | Pilot flexibility-score improvement of 0.2-0.5/5, triangulated with changeover or waiting time. | External n=52 sensor-priority reference + toolkit scenario (P)
4 | high | KPI-I-01 | I | 关键测点与设备/批次/工单映射完整率 | Completeness of tag-to-asset/batch/work-order mapping | 2.5768 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 当前集成能力决定统计结果能否回到具体业务情境。 | Integration determines whether analysis can be traced back to business context. |  |  | Toolkit operating target (P)
5 | high | KPI-O-01 | O | 异常闭环按期完成率 | On-time exception closure rate | 2.6725 | 现场数据待确认 / Operational baseline required | 80 | 90 | % | higher | 12 weeks / 12周试点 | 优化层先验证规则和行动闭环，再进入高级模型。 | Optimisation should validate rules and action closure before advanced models. |  |  | Toolkit operating target (P)
6 | high | KPI-P-01 | P | 关键测点有效覆盖率 | Valid coverage of critical tags | 2.7767 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 感知层是后续连接、集成和优化的输入门槛。 | Perception is the input gate for connectivity, integration, and optimisation. |  |  | External n=52 Sensor_Inf=4.5077 reference + project score
7 | medium | KPI-H-01 | H | 目标岗位任务验证通过率 | Task-based competence pass rate for target roles | 2.8615 | 现场数据待确认 / Operational baseline required | 90 | 95 | % | higher | 12 weeks / 12周试点 | 培训完成不等于会用，以真实任务验证人机协同能力。 | Training completion is not competence; verify with real tasks. |  |  | Toolkit operating target (P)
8 | medium | KPI-C-01 | C | 试点数据采集可用率 | Pilot data-acquisition availability | 2.7857 | 现场数据待确认 / Operational baseline required | 97 | 99 | % | higher | 12 weeks / 12周试点 | 用链路可用率代替“已联网”这一不可审计描述。 | Use measurable link availability rather than a binary 'connected' claim. |  |  | Toolkit operating target (P)

## ROI_Calculator
Editable ROI Calculator / 可编辑 ROI 快速估算
Investment / 投资 | 180000
Annual addressable value / 年度可改善价值池 | 1500000
Annual operating cost / 年度运维成本 | 30000
Improvement low % / 改善下限 | 5%
Improvement high % / 改善上限 | 10%
Horizon years / 评估年数 | 3
Scenario | Improvement | Gross benefit/year | Net benefit/year | Payback months | ROI over horizon
Conservative
Base
Optimistic
Break-even improvement / 盈亏平衡改善率
Boundary / 边界 | 回收期为简单静态估算，未计税、折旧、资金成本、停产损失或爬坡曲线。 / Payback is a simple static estimate excluding tax, depreciation, cost of capital, downtime, and ramp-up.